## Gantt Chart Template
GANTT CHART | [27 empty] | https://goo.gl/PXLbMe
Task Number | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Software Requirements
1.1 | Introduction | Ahmad | 2025-02-07 | 2025-02-28 | 21 | 100% | bar: WEEK 1 W to WEEK 3 W
1.2 | Non & Functional Requirements | Fizan | 2025-02-07 | 2025-02-28 | 21 | 100% | bar: WEEK 1 W to WEEK 3 W
1.3 | Data Description | Tom/Ahmad | 2025-02-12 | 2025-02-28 | 16 | 100% | bar: WEEK 1 W to WEEK 3 W
1.4 | Interface & UI Diagrams | Zakir | 2025-02-07 | 2025-02-28 | 21 | 100% | bar: WEEK 1 W to WEEK 3 M
1.5 | Literature Review | Zakir/Fizan | 2025-02-07 | 2025-02-28 | 21 | 100% | bar: WEEK 1 W to WEEK 3 W
1.6 | UML + USE CASE | Zakir/Dan | 2025-02-07 | 2025-02-28 | 21 | 100% | bar: WEEK 1 W to WEEK 3 W
1.7 | LSEPI & Risk Assessment | Murtaza | 2025-02-12 | 2025-02-28 | 16 | 100% | bar: WEEK 1 W to WEEK 3 W
1.8 | Peer Review | Everyone | 2025-02-18 | 2025-02-28 | 10 | 100% | bar: WEEK 2 M to WEEK 3 W
2 | Initial Implementation (Demo Build)
2.1 | HTML Pages (5) | Ali | 2025-02-26 | 2025-03-05 | 9 | 100% | bar: WEEK 2 M to WEEK 3 W
2.2 | CSS Style | Zakir | 2025-02-26 | 2025-03-05 | 9 | 100% | bar: WEEK 2 M to WEEK 4 R
2.3 | Access levels (Roles) | Tom | 2025-02-26 | 2025-03-05 | 9 | 100% | bar: WEEK 2 M to WEEK 4 R
2.4 | Project & Task Create/Display/Edit | Tom | 2025-02-26 | 2025-03-05 | 9 | 100% | bar: WEEK 2 M to WEEK 4 R
3 | Final Implementation
3.1 | Refine HTML & CSS | Ali/Zakir | 2025-01-03 | 2025-02-04 | 31 | 100% | bar: WEEK 2 M to WEEK 7 T
3.2 | Project Logs | Dan | 2025-01-03 | 2025-02-04 | 31 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 3 W to WEEK 7 T
3.3 | Dashboard | Fizan | 2025-01-03 | 2025-02-04 | 31 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 3 W to WEEK 7 T
3.4 | Email Notifications | Murtaza | 2025-01-03 | 2025-02-04 | 31 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 3 W to WEEK 7 T
3.5 | Export Function | Zakir | 2025-01-03 | 2025-02-04 | 31 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 3 W to WEEK 7 T
3.6 | System Logs | Tom | 2025-01-03 | 2025-02-04 | 31 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 3 W to WEEK 7 T
4 | Unit Testing
4.1 | Error handling | Fizan | 2025-01-03 | 2025-02-04 | 31 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 3 W to WEEK 7 T
4.2 | Database Testing | Ahmad | 2025-01-03 | 2025-02-04 | 0 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 3 W to WEEK 7 T
5 | Release | bar: WEEK 2 M to WEEK 2 F

## Try Smartsheet
Try Smartsheet for Free